## Backlog Report
CSC301
Theme | ID | User Story | Acceptance Criteria | Comments | Sprint | Status | Points | Priorities: Ranking from 1 - 10, the higher the number, the higher the priority
Charity App Product Backlog | PDT1 | As Jon I want to be able to login to my profile using my Facebook or Gmail account that is already associated with my Android phone So I can not have to create an additional new username and password just for this app. | a) I can simply enter my facebook/gmail and password and access the app | Feature: Login/Signup (Gmail, Facebook, or own authentication service) | Sprint 2 | Completed | 21 | 6
| PDT2 | As Carl I want to generate money for my favourite charities through watching adds So I can give to charity, with out taking money out of my own pocket because I am broke | a) I can apply the points that I have earned from the ads that I watched to my favourite charity without spending my own money. | Implement Google Admob | Sprint 2 | Completed | 21 | 6
| PDT3 | As Carl I want to be able to create and edit my user profile data So I can make the profile my own | a) Profile for each user | Create user profile page | Sprint 2 | Completed | 13 | 6
| PDT4 | As product Owner I want to have all the user's profile information saved securily So I can: not get sued for loosing user info | a) In my points balance, I can see how much it converts to in real world currency | Be able to create/edit user profile data in the firebase json objects | Sprint 2 | Completed | 13 | 1
| PDT6 | As Margaret I want to know what events they have held in the past So I can know if the revenue they spent towards events is really being used in a way I would like to support. | a) When I select a charity, I can see many things about that charity Including their events history | Feature: Event Sign Up | Sprint 3 | In progress | 13 | 2
| PDT8 | As Jon I want to see each charity's logo So I can immediately recognize an organization so I get to read titles as passively as possible. while I sip my morning coffee | a) when i scroll down the list of charities, i can see their logo beside their name | Implement: Get and display the organization's logo | Sprint 1 | Completed | 40 | 7
| PDT9 | As Margaret I want to host a lung cancer awareness BBQ So I can raise money for lung cancer research | a) I can make an event, state the description of my event, mention the time and where it is taking place | Feature: Create an event (need to categorize same as the charities) | Sprint 2 | Completed | 21 | 7
| PDT10 | As Carl I want to have a clean UI/UX experience So I can easily navigate within the app pages | a) I can leave a rating and a review about a particular event that I attended | Create UI/UX experience for user navigation between different pages of the app | Sprint 2 | Completed | 8 | 5
| PDT12 | As Margaret I want to let the local homeless shelter near my university know I am coming to help out at their Christmas soup kitchen free food giveaway So I can share my amazing cooking with the homeless and have some company | a) I can find charities near me including a homeless shelter within the app and notify that I intend to attend | Feature: Event Sign Up | Sprint 2 | Completed | 8 | 7
| PDT13 | As Carl I want to only see charitable events happening around me, without needing to see all the organisations who are always located near by So I can just get necessary volunteer hours to put on my resume | a) I can view charities near me, max 8 charities at a time | On the home screen have two buttons, events and charities, once they select, the rest of the UI would be the same, just have different queries on the backend | Sprint 1 | Completed | 8 | 6
| PDT14 | As Carl I want to to be able to turn location services on and off anytime So I can control when I want to share my location in order to find charities near me | a) i can choose when I want my location to be serviced | Ability to toggle location services on or off | Sprint 1 | Completed | 13 | 9
| PDT15 | As Margaret I want to be able to look up charities based on my current address So I can accurately find the charities near me | a) When I turn on location services, I can see a map that shows my current location and the charities around me within a given radius. and also a list view | Enter current address and list all nearby charities | Sprint 1 | Completed | 40 | 9
| PDT16 | As Margaret I want to be able to find accurate directions from my current location to a charity So I can get to their location without getting lost | a) When I select a charity, I can find out how to get there from my current location and have the option to see how to get there via driving, walking, transit | Directions from current address to charity | Sprint 1 | Completed | 13 | 10
| PDT17 | As Carl I want to be able to control the zoom of the map of charities So I can zoom in and out to help me find my location and the charity I'm interested in | a) when i pinch my fingers on the map or press the minus button, the map zooms out and vice versa whenI do the opposite | Zoom in and out of the charity map | Sprint 1 | Completed | 21 | 2
| PDT18 | As Jon I want to be able to see all the infromation of the charity on one page So I can easiler do my research on the charity. | a) Profile page for each charity which shows all the social media, website, donation, summary, and logo | Integrate the social media, website, donation links, summary and logo scraping into 1 activity | Sprint 2 | Completed | 21 | 9
| PDT19 | As Carl I want to be able to filter charities based on their radius from my current location So I can find the charities that require the least amount of travelling | a) Able to only see a subset of charities that are within x radius of the current location | Get all the longitude and latitude values of each charity's location | Sprint 2 | Completed | 40 | 10
| PDT20 | As Margaret I want to visualise charities on the map as pins So I can easily spot them on the map | a) When I turn on location services, I can see a map that shows my current location and the charities around me as pins | Visualize charities as pins | Sprint 1 | Completed | 21 | 10
| PDT21 | As product owner I want to migrate charity data to sql database So I can get the data more effeicently when qeuring | a) Data is in a sql database instead of firebase | Migrate charity data into sql database | Sprint 2 | Completed | 20 | 5
| PDT22 | As Jon I want to view a quick summary of the charity I am interested in while on the way to work So I can decide if I want to donate to it or not | a) When I select a charity I can see many things about that charity including their summary | Implement charity summary | Sprint 1 | Completed | 40 | 8
| PDT23 | As Margaret I want to be able to click a "more info" button So I can find out more information about the company I want to donate to | a) I can click a Button that links to organisation website if available | Implement "more info" button | Sprint 1 | Completed | 40 | 8
| PDT24 | As Margaret I want to be able to easily click a "donate" button So I can donate to the organisation using the credit Carl her nephew got for her | a) Donate button gives a link to the donate page of the charity | implement a "Donate" button | Sprint 1 | Completed | 40 | 7
| PDT25 | As Carl, Jon I want to be able to click the "social media" button So I can get access to an organisation on social media to get alerts during their busy day. | a) Social media button gives a link to the social media of the organisation if available | Implement a "Social media" button | Sprint 1 | Completed | 40 | 7
| PDT26 | As Jon I want to be able to pull up financial data about an organisation I am interested in So I can be more financially informed about that organisation and better decide if they should have my money | a) Show pretty stats about the organization finances | Need to hash out what that would look like. | Sprint 1 | Completed | 40 | 9
| PDT27 | As Margaret I want to be able to see the vision/opinions of an organisation So I can decide if or not my vision/opinions are conservative. | a) Show the ways the organization is allocating their resources | Need to flesh out how this will be shown. | Sprint 1 | Completed | 40 | 9
| PDT28 | As the product owner I want to have address, name, postal code, type and category changed into json format So I can have it easily passed on to the UI in form of data about company summaries, addresses and other information | a) Parse address, name, postal code, type and category from data file | Clean up the dataset to remove inactive organizations | Sprint 1 | Completed | 21 | 10
| PDT29 | As the product owner I want to Integrate database in Android App (Firebase) So I can have data on companies easily available and updated in real time | a) If a new charity was built near me, my query to includes this new charity |  | Sprint 1 | Completed | 13 | 8
| PDT30 | As Jon I want to Get compensation and revenue expense data of organisations for all years available So I can view the financial legitimacy of the company I am interested in donating to | a) When I select a charity I can see many things about that charity including proof of their financial legitimacy |  | Sprint 1 | Completed | 21 | 5
| PDT31 | As Margaret I want to be able to just look up “adopt cat” and all the charities pertaining to that would pop up So I can donate to charities that help people adopt cats. | a) I can search for a charity using a keyword and return a list of charities related to that keyword | Use the search feature from the Canada revenue website as our search feature in the app | Sprint 2 | Completed | 40 | 2
| PDT32 | Register with own email account and specifying first and last names | a) Users can register through the application and the info gets stored in a database | Let the user sign up the traditional way using their emails instead of connecting their Facebook or Gmail accounts | Sprint 3 | In progress | 7 | 7
| PDT33 | Display secondary search bar when user intends to search, bottom search bar acts as the location-filter, top search bar acts as the general-filter |  |  | Sprint 3 | In progress | 21 | 4
| PDT34 | Auto log in after logging in for the first time |  |  | Sprint 3 | In progress | 7 | 5
| PDT35 | "Skip log in screen" button |  |  | Sprint 3 | In progress | 7 | 5
| PDT36 | Add a profile sandwich button |  |  | Sprint 3 | In progress | 7 | 7
| PDT37 | Move refresh and center-on-location button to bottom |  |  | Sprint 3 | In progress | 7 | 4
| PDT38 | Add a charity/event toggle below search bar |  |  | Sprint 3 | In progress | 14 | 6
| PDT39 | Add category picker button on search bar, options for selecting categories pop up when pressed |  |  | Sprint 3 | In progress | 14 | 8
| Total for theme 'Charity App Product Backlog ' |  |  | 774.0 points
Total for backlog 'CSC301' |  |  |  | 774.0 points

## Story List
Theme | ID | User Story | Acceptance Criteria | Comments | Sprint | Status | Points
Charity App Product Backlog | PDT1 | As Jon I want to be able to login to my profile using my Gmail account that is already associated with my Android phone So I can not have to create an additional new username and password just for this app. | a) I can simply enter my gmail and password and access the app | Feature: Login/Signup (Gmail, Facebook, or own authentication service) | Sprint 2 | To do | 21.0
Charity App Product Backlog | PDT2 | As Carl I want to generate money for my favourite charities through watching adds So I can give to charity, with out taking money out of my own pocket because I am broke | a) I can apply the points that I have earned from the ads that I watched to my favourite charity without spending my own money. | Implement Google Adsense | Sprint 2 | To do | 21.0
Charity App Product Backlog | PDT3 | As Carl I want to keep track of how much revenue I have generated by watching ads So I can allocate the appropriate amount of money to charitably organizations of the my choice. | a) I can see my current points balance | Implement user profile points system for watching ads | Sprint 2 | To do | 13.0
Charity App Product Backlog | PDT4 | As Carl I want to know how much the in app points I generated are worth in real world currency So I can know how much I am donating financially to Ducks Unlimited. | a) In my points balance, I can see how much it converts to in real world currency | Implement how in app points translated to charitable donations | Sprint 2 | To do | 13.0
Charity App Product Backlog | PDT5 | As Margaret I want to know how organised the people hosting the "Run for the Cure" diabetes event are So I can know whether I should go help volunteer. | a) When I select a charity, I can see its ratings and reviews | Feature: Event organization rating system (just the average of all the ratings given from past events) | Sprint 2 | To do | 20.0
Charity App Product Backlog | PDT6 | As Margaret I want to know what events they have held in the past So I can know if the revenue they spent towards events is really being used in a way I would like to support. | a) When I select a charity, I can see many things about that charity Including their events history | Feature: Event sign up/organized history | Sprint 2 | To do | 13.0
Charity App Product Backlog | PDT7 | As Carl I want to everyone to know what I still look like So I can get the social recognition from my friends for helping feed the homeless at the local shelter. | a) I can upload a picture that represents my profile | Implement: Upload Profile Picture |  |  | 13.0
Charity App Product Backlog | PDT8 | As Jon I want to see each charity's logo So I can immediately recognize an organization so I get to read titles as passively as possible. while I sip my morning coffee | a) when i scroll down the list of charities, i can see their logo beside their name | Implement: Get and display the organization's logo | Sprint 1 | Completed | 40.0
Charity App Product Backlog | PDT9 | As Margaret I want to host a lung cancer awareness BBQ So I can raise money for lung cancer research | a) I can make an event, state the description of my event, mention the time and where it is taking place | Feature: Create an event (need to categorize same as the charities) | Sprint 2 | To do | 21.0
Charity App Product Backlog | PDT10 | As Carl I want to let others know how much I enjoyed the computer science charity event So I can help him out by letting others know next years event will likely be worth attending. | a) I can leave a rating and a review about a particular event that I attended | Feature: Event Rating | Sprint 2 | To do | 8.0
Charity App Product Backlog | PDT12 | As Margaret I want to let the local homeless shelter near my university know I am coming to help out at their Christmas soup kitchen free food giveaway So I can share my amazing cooking with the homeless and have some company | a) I can find charities near me including a homeless shelter within the app and notify that I intend to attend | Feature: Event Sign Up | Sprint 2 | To do | 8.0
Charity App Product Backlog | PDT13 | As Carl I want to only see charitable events happening around me, without needing to see all the organisations who are always located near by So I can just get necessary volunteer hours to put on my resume | a) I can view charities near me, max 8 charities at a time | On the home screen have two buttons, events and charities, once they select, the rest of the UI would be the same, just have different queries on the backend | Sprint 1 | Completed | 8.0
Charity App Product Backlog | PDT14 | As Carl I want to to be able to turn location services on and off anytime So I can control when I want to share my location in order to find charities near me | a) i can choose when I want my location to be serviced | Ability to toggle location services on or off | Sprint 1 | Completed | 13.0
Charity App Product Backlog | PDT15 | As Margaret I want to be able to look up charities based on my current address So I can accurately find the charities near me | a) When I turn on location services, I can see a map that shows my current location and the charities around me within a given radius. and also a list view | Enter current address and list all nearby charities | Sprint 1 | Completed | 40.0
Charity App Product Backlog | PDT16 | As Margaret I want to be able to find accurate directions from my current location to a charity So I can get to their location without getting lost | a) When I select a charity, I can find out how to get there from my current location and have the option to see how to get there via driving, walking, transit | Directions from current address to charity | Sprint 2 | To do | 40.0
Charity App Product Backlog | PDT17 | As Carl I want to be able to control the zoom of the map of charities So I can zoom in and out to help me find my location and the charity I'm interested in | a) when i pinch my fingers on the map or press the minus button, the map zooms out and vice versa whenI do the opposite | Zoom in and out of the charity map |  |  | 21.0
Charity App Product Backlog | PDT18 | As Jon I want to be able to adjust my search radius So I can view more or less charities around me depending on their distance from my current location | a) I can change the search radius from 5km to 1km and return a list of charities that doesn't include make-a-wish because make-a-wish is 4km from where I am | Adjust search radius | Sprint 2 | To do | 21.0
Charity App Product Backlog | PDT19 | As Carl I want to be able to filter charities based on their radius from my current location So I can find the charities that require the least amount of travelling | a) I can change the search radius from 5km to 1km and return a list of charities that doesn't include make-a-wish because make-a-wish is 4km from where I am | Find charities based on radius | Sprint 2 | To do | 40.0
Charity App Product Backlog | PDT20 | As Margaret I want to visualise charities on the map as pins So I can easily spot them on the map | a) When I turn on location services, I can see a map that shows my current location and the charities around me as pins | Visualize charities as pins | Sprint 1 | Completed | 21.0
Charity App Product Backlog | PDT21 | As Carl, Jon I want to be able to drag a pin around which represents my location So I can change my location with ease | a) I can drag the pin that represents my current location and the app uses that as my new current lcoation | Drag a pin around the map to change locations | Sprint 2 | To do | 20.0
Charity App Product Backlog | PDT22 | As Jon I want to view a quick summary of the charity I am interested in while on the way to work So I can decide if I want to donate to it or not | a) When I select a charity I can see many things about that charity including their summary | Implement charity summary | Sprint 1 | Completed | 40.0
Charity App Product Backlog | PDT23 | As Margaret I want to be able to click a "more info" button So I can find out more information about the company I want to donate to | a) I can click a Button that links to organisation website if available | Implement "more info" button | Sprint 1 | Completed | 40.0
Charity App Product Backlog | PDT24 | As Margaret I want to be able to easily click a "donate" button So I can donate to the organisation using the credit Carl her nephew got for her | a) Donate button gives a link to the donate page of the charity | implement a "Donate" button | Sprint 1 | Completed | 40.0
Charity App Product Backlog | PDT25 | As Carl, Jon I want to be able to click the "social media" button So I can get access to an organisation on social media to get alerts during their busy day. | a) Social media button gives a link to the social media of the organisation if available | Implement a "Social media" button | Sprint 1 | Completed | 40.0
Charity App Product Backlog | PDT26 | As Jon I want to be able to pull up financial data about an organisation I am interested in So I can be more financially informed about that organisation and better decide if they should have my money | a) Show pretty stats about the organization finances | Need to hash out what that would look like. | Sprint 1 | Completed | 40.0
Charity App Product Backlog | PDT27 | As Margaret I want to be able to see the vision/opinions of an organisation So I can decide if or not my vision/opinions are conservative. | a) Show the ways the organization is allocating their resources | Need to flesh out how this will be shown. | Sprint 1 | Completed | 40.0
Charity App Product Backlog | PDT28 | As the product owner I want to have address, name, postal code, type and category changed into json format So I can have it easily passed on to the UI in form of data about company summaries, addresses and other information | a) Parse address, name, postal code, type and category from data file | Clean up the dataset to remove inactive organizations | Sprint 1 | Completed | 21.0
Charity App Product Backlog | PDT29 | As the product owner I want to Integrate database in Android App (Firebase) So I can have data on companies easily available and updated in real time | a) If a new charity was built near me, my query to includes this new charity |  | Sprint 1 | Completed | 13.0
Charity App Product Backlog | PDT30 | As Jon I want to Get compensation and revenue expense data of organisations for all years available So I can view the financial legitimacy of the company I am interested in donating to | a) When I select a charity I can see many things about that charity including proof of their financial legitimacy |  | Sprint 1 | Completed | 21.0
Charity App Product Backlog | PDT31 | As Margaret I want to be able to just look up “adopt cat” and all the charities pertaining to that would pop up So I can donate to charities that help people adopt cats. | a) I can search for a charity using a keyword and return a list of charities related to that keyword |  |  |  | 40.0